## BCM_Register
BCM ID | Business Function | Department | BCM Owner | Risk Scenario | Recovery Strategy | RTO | RPO | Last Test | Status
BCM-001 | VPN Services | Network | Ahmed | ISP Failure | Secondary ISP | 20 min | 10 min | 2026-06-15 | Active
BCM-002 | Firewall Cluster | Security | Sara | Firewall Failure | HA Cluster | 15 min | 5 min | 2026-06-20 | Active
BCM-003 | Wireless Network | Network | Omar | Controller Failure | Backup Controller | 1 hr | 30 min | 2026-05-18 | Active
BCM-004 | Cisco ISE | IAM | Khalid | Authentication Failure | DR ISE | 30 min | 15 min | 2026-04-25 | Review
BCM-005 | TACACS Server | Security | Faisal | AAA Failure | Secondary Server | 30 min | 15 min | 2026-06-02 | Active

## BCM_Exercises
Exercise ID | Exercise Type | Scenario | Participants | Result | Lessons Learned | Next Test
EX-001 | Tabletop | Ransomware | SOC + IT | Passed | Improve escalation | 2026-10-01
EX-002 | Technical | Data Center Failure | Infra Team | Passed | Faster DNS failover | 2026-11-15
EX-003 | Functional | ISP Outage | Network Team | Partial | Improve communication | 2026-12-01
EX-004 | Full Simulation | Regional Disaster | All Teams | Passed | Recovery met SLA | 2027-01-20